## Project
[YOUR COMPANY NAME]
CCTV Commissioning & Handover Record
Field of view simulations produced using FOV Pro · fovpro.app
PROJECT DETAILS
Project / site name
Site address
Client
Head contractor (if applicable)
Proposal / acceptance reference
FOV Pro project report reference
Commissioned by
Date of commissioning
Date of handover
SUMMARY — CALCULATES FROM THE COMMISSIONING SHEET
Cameras recorded | 0
Passed | 0
Failed | 0
Incomplete | 0
Field of view variations agreed with client | 0
Open defects | 0
PURPOSE
This record documents the commissioning of each installed camera against the coverage the client accepted before installation. The FOV Pro project report carries the capture for every position; this workbook records the checks against each one.
The first two checks are the ones that matter at handover: either the installed camera delivers the coverage the client accepted, or it doesn't and a variation was agreed. Recording that at commissioning stops it being discovered at practical completion.
Where the head contractor mandates their own ITP format, this is the supporting evidence for the field of view and commissioning checks rather than a replacement for it.
HOW TO USE THIS WORKBOOK
Blue text on a cream cell | Your input.
Dropdown cells | Y / N, or Pass / Fail / NA. Click the cell and pick from the list.
Result column | Calculates itself — PASS, FAIL or INCOMPLETE. A blank check counts as incomplete.
Row 5 on Commissioning | A worked example. Overwrite it or delete it before issuing.
More than 50 cameras | Copy the last row down — dropdowns and formatting come with it. Extend the summary ranges to match.
Checks | Rename the column headings to match your own procedure. Keep them the same for every camera on the project.
Captures | Enter the page or capture number from the FOV Pro project report, and attach the report to this record.
Template supplied by FOV Pro: fovpro.app. Replace the bracketed placeholders and apply your own branding before issuing.

## Commissioning
[YOUR COMPANY NAME] — CCTV Commissioning Record
One row per camera. Result calculates itself. Fail cells turn red.
CAMERA |  |  |  |  | FIELD OF VIEW |  |  | COMMISSIONING CHECKS | [12 empty] | SIGN-OFF
# | Camera ref / channel | Camera model | Location | FOV Pro capture ref | Installed FOV matches accepted coverage | If no — variation agreed with client | Variation ref | Model and location as per schedule | Mounting secure, height and angle as recorded | Focus / image sharpness | Frame rate (fps) | Recording resolution | Motion detection configured | Motion / privacy masking configured | Recording and playback verified | Day / night switching verified | Time and date synchronised | Channel number and labelling correct | Remote viewing verified | RESULT | Commissioned by | Date | Notes
e.g. | CH01 | Hikvision DS-2CD2387G2-LU | Main entry — external | p.3 | Y | NA |  | Pass | Pass | Pass | 25 | 8MP | Pass | Pass | Pass | Pass | Pass | Pass | Pass | PASS | J. Smith | 2026-10-05 | Example row — overwrite or delete
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Defects
Outstanding items and defects
Record any check marked Fail, and any other item open at handover, with the agreed rectification.
# | Camera ref | Check failed | Description | Agreed rectification | Responsible | Target date | Closed date | Status
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Handover
Handover
Review with the client, together with the Commissioning sheet and the attached FOV Pro project report.
STATUS AT HANDOVER
Cameras recorded | 0
Passed | 0
Failed | 0
Incomplete | 0
FOV variations agreed with client | 0
Open defects | 0
CLIENT CONFIRMATION
• The installed coverage for each camera position has been reviewed against the coverage accepted prior to installation.
• Where installed coverage differs from the accepted coverage, the variation has been agreed and recorded.
• The commissioning checks recorded in this workbook have been demonstrated.
• Any outstanding items are recorded on the Defects sheet, with an agreed rectification date.
• The system has been handed over, subject to those outstanding items.
Client / head contractor representative |  | [Your company name] representative
Name |  | Name
Position |  | Position
Signature |  | Signature
Date |  | Date